CONSULTING DOCUMENT

Consulting Methodology

A structured approach from baseline assessment to embedded procurement ESG capability.

| Service package | Procurement Sustainability & ESG Transformation |
| --- | --- |
| Target clients | UAE manufacturing companies; healthcare organizations; infrastructure contractors; industrial businesses |

# Methodology Overview

The methodology is designed for operational procurement environments where ESG ambition must translate into sourcing decisions, supplier obligations, project controls, and measurable data.

| Phase | Purpose | Key activities | Decision gate |
| --- | --- | --- | --- |
| 1. Mobilize | Confirm objectives, governance, stakeholders, categories, and data access. | Kickoff, document request, stakeholder map, workplan. | Scope and success measures confirmed. |
| 2. Diagnose | Establish current-state procurement ESG maturity and risk exposure. | Policy review, spend and supplier segmentation, interviews, contract sample review. | Baseline accepted. |
| 3. Design | Create practical operating model, tools, and criteria. | Sourcing criteria, scorecard, policy, tender clauses, reporting template. | Toolkit approved for pilot. |
| 4. Pilot | Test tools on priority categories or projects. | Supplier engagement, data collection, bid evaluation, corrective actions. | Pilot lessons and refinements agreed. |
| 5. Embed | Institutionalize governance, cadence, ownership, and KPIs. | Training, playbook handover, dashboard design, roadmap. | Steady-state ownership transferred. |

# Workstreams

| Workstream | Scope | Typical evidence reviewed |
| --- | --- | --- |
| Governance and policy | Decision rights, approvals, sustainability obligations, procurement roles. | Policies, delegation of authority, committee packs. |
| Category and spend risk | ESG risk by category, geography, criticality, and supplier dependency. | Spend extracts, supplier master, category plans. |
| Supplier due diligence | Supplier questionnaires, audit history, certifications, corrective action process. | Supplier files, onboarding records, audit reports. |
| Sourcing and contracting | RFP criteria, evaluation weighting, contract ESG clauses, lifecycle controls. | Tender packs, bid evaluations, contract templates. |
| Data and reporting | ESG data capture, carbon reporting, evidence retention, management reporting. | Dashboards, spreadsheets, ERP fields, reporting packs. |

# Governance Rhythm

Weekly project working session to resolve data, stakeholder, and design issues.

Fortnightly steering checkpoint to approve scope decisions and remove blockers.

Pilot review session to validate usability with procurement, sustainability, finance, legal, and operations.

Final handover covering tools, ownership, KPIs, and the 90-day implementation plan.

# Quality Principles

Commercially practical: ESG requirements are tied to category risk and supplier leverage.

Evidence-based: recommendations are linked to reviewed documents, interviews, spend data, and supplier samples.

Auditable: templates create a clear trail from requirement to evaluation to supplier action.

Proportionate: high-risk categories receive deeper due diligence; low-risk purchases remain efficient.