ADVISORY TOOLKIT

ESG Gap Analysis Template

Structured gap register and corrective action tracker

| Field | Details |
| --- | --- |
| Prepared by | SCP Business Advisory |
| Audience | UAE private sector companies, including SMEs and owner-managed businesses |
| Use | Client advisory, internal assessment, implementation planning and evidence collection |
| Version | June 2026 |

Consultant note: This document is a practical advisory aid. It should be tailored to the client entity, emirate-level permits, sector regulations, contracts and any implementing decisions issued under UAE climate legislation.

# Gap Analysis Instructions

Use this template after the readiness assessment. The consultant should record the current state, desired state, evidence reviewed, priority, corrective action and responsible owner.

| Area | Current state | Target state | Priority | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- | --- |
| Climate governance | No formal ESG owner | Named owner and quarterly review | High | Appoint ESG owner and approve terms of reference | GM / Owner | 30 days |
| GHG data | Invoices available but not consolidated | Monthly Scope 1 and 2 data file | High | Create emissions data log and evidence folder | Finance / Ops | 60 days |
| Risk management | Climate risks not in risk register | Climate risks rated and reviewed | Medium | Add heat, water, flood and customer transition risks | Risk owner | 45 days |

# Gap Rating Guide

High: regulatory exposure, customer tender requirement, material cost or safety impact.

Medium: important control improvement with manageable implementation effort.

Low: enhancement, documentation improvement or future reporting maturity item.

# Evidence Review Log

| Document reviewed | Date | Owner | Finding | Follow-up |
| --- | --- | --- | --- | --- |

# Client Tailoring and Evidence Pack

Before issuing this document to a client, replace bracketed fields, confirm the client legal entity name, emirate, licence activity, facilities, sector permits and reporting period. For multi-site clients, prepare one consolidated version plus site-level evidence where the data is materially different.

Authority roles: MOCCAE sets federal climate and environmental policy direction, guidance and national frameworks. Local authorities and regulators, such as Dubai Municipality, Environment Agency - Abu Dhabi (EAD), relevant emirate environmental bodies and Free Zone Authorities including Umm Al Quwain Free Zone or JAFZA, typically administer local environmental permits, inspections, facility-level compliance and sector-specific requirements.

| Tailoring area | What to confirm | Suggested owner |
| --- | --- | --- |
| Company profile | Trade licence, activity list, site list, ownership and operating boundary. | Admin / Legal |
| Compliance context | Applicable UAE federal law, MOCCAE guidance, emirate permits, local inspection requirements, customer requirements, free-zone rules and tender clauses. | Consultant / Compliance |
| Evidence folder | Utility bills, fuel records, waste tickets, HR records, policies, minutes, photos and calculations. | ESG Lead |
| Approval record | Management sign-off, version control, review date and action owners. | Managing Director |

Evidence standard: For every claim, score, action or risk rating, keep a source file or management note. This reduces greenwashing risk and makes the toolkit useful for customer due diligence, tenders, bank requests and regulatory enquiries.

# Reference Sources for Tailoring

UAE Legislation platform, Environment and Natural Resources category, including legislation on safeguarding the environment and reducing the negative effects of climate change.

UAE Ministry of Climate Change and Environment mandate, including climate policy, strategies and initiatives supporting the UAE Net Zero 2050 Strategy.

UAE Net Zero by 2050 Strategic Initiative and UAE Nationally Determined Contribution direction for emissions reduction.

GHG Protocol Corporate Standard and Scope 2 Guidance for organisational greenhouse gas accounting.

ISSB IFRS S1 and IFRS S2, GRI Standards and local market ESG reporting guidance where applicable to listed entities or customer requirements.