ADVISORY TOOLKIT

Climate Compliance Roadmap

90-day to 12-month implementation plan for UAE SMEs

| Field | Details |
| --- | --- |
| Prepared by | SCP Business Advisory |
| Audience | UAE private sector companies, including SMEs and owner-managed businesses |
| Use | Client advisory, internal assessment, implementation planning and evidence collection |
| Version | June 2026 |

Consultant note: This document is a practical advisory aid. It should be tailored to the client entity, emirate-level permits, sector regulations, contracts and any implementing decisions issued under UAE climate legislation.

# Roadmap Overview

This roadmap is designed for a UAE SME that needs to become climate-compliance ready without creating unnecessary bureaucracy.

| Phase | Timing | Main activities | Outputs |
| --- | --- | --- | --- |
| Phase 1: Mobilise | Weeks 1-4 | Appoint owner, map obligations, collect utility and fuel records. | ESG owner, evidence folder, data request list. |
| Phase 2: Baseline | Weeks 5-10 | Calculate Scope 1 and Scope 2 baseline, identify key risks. | GHG baseline, risk register, quick wins. |
| Phase 3: Controls | Months 3-6 | Approve policy, governance routine, data controls and supplier clauses. | Policy pack, monthly dashboard, supplier checklist. |
| Phase 4: Reduce | Months 6-12 | Implement energy, fleet, cooling, waste and procurement actions. | Action plan progress, capex decisions, reduction evidence. |
| Phase 5: Report | Annual | Prepare management report and customer/regulator response pack. | ESG report inputs, management presentation. |

# 90-Day Sprint Plan

| Week | Action | Owner | Success measure | Status |
| --- | --- | --- | --- | --- |
| 1 | Kickoff and site/data map | Consultant + ESG owner | Site list and data request issued | Open |
| 2 | Collect invoices and fleet data | Finance / Ops | 12 months data received | Open |
| 3 | Initial GHG baseline | Consultant | Draft calculation workbook | Open |
| 4 | Climate and ESG risk workshop | Management | Risk register draft | Open |
| 5 | Management review | GM / Owner | Approved roadmap | Open |

# Client Tailoring and Evidence Pack

Before issuing this document to a client, replace bracketed fields, confirm the client legal entity name, emirate, licence activity, facilities, sector permits and reporting period. For multi-site clients, prepare one consolidated version plus site-level evidence where the data is materially different.

Authority roles: MOCCAE sets federal climate and environmental policy direction, guidance and national frameworks. Local authorities and regulators, such as Dubai Municipality, Environment Agency - Abu Dhabi (EAD), relevant emirate environmental bodies and Free Zone Authorities including Umm Al Quwain Free Zone or JAFZA, typically administer local environmental permits, inspections, facility-level compliance and sector-specific requirements.

| Tailoring area | What to confirm | Suggested owner |
| --- | --- | --- |
| Company profile | Trade licence, activity list, site list, ownership and operating boundary. | Admin / Legal |
| Compliance context | Applicable UAE federal law, MOCCAE guidance, emirate permits, local inspection requirements, customer requirements, free-zone rules and tender clauses. | Consultant / Compliance |
| Evidence folder | Utility bills, fuel records, waste tickets, HR records, policies, minutes, photos and calculations. | ESG Lead |
| Approval record | Management sign-off, version control, review date and action owners. | Managing Director |

Evidence standard: For every claim, score, action or risk rating, keep a source file or management note. This reduces greenwashing risk and makes the toolkit useful for customer due diligence, tenders, bank requests and regulatory enquiries.

# Reference Sources for Tailoring

UAE Legislation platform, Environment and Natural Resources category, including legislation on safeguarding the environment and reducing the negative effects of climate change.

UAE Ministry of Climate Change and Environment mandate, including climate policy, strategies and initiatives supporting the UAE Net Zero 2050 Strategy.

UAE Net Zero by 2050 Strategic Initiative and UAE Nationally Determined Contribution direction for emissions reduction.

GHG Protocol Corporate Standard and Scope 2 Guidance for organisational greenhouse gas accounting.

ISSB IFRS S1 and IFRS S2, GRI Standards and local market ESG reporting guidance where applicable to listed entities or customer requirements.