ADVISORY TOOLKIT

ESG Action Plan

Practical implementation tracker with quick wins and monthly review

| Field | Details |
| --- | --- |
| Prepared by | SCP Business Advisory |
| Audience | UAE private sector companies, including SMEs and owner-managed businesses |
| Use | Client advisory, internal assessment, implementation planning and evidence collection |
| Version | June 2026 |

Consultant note: This document is a practical advisory aid. It should be tailored to the client entity, emirate-level permits, sector regulations, contracts and any implementing decisions issued under UAE climate legislation.

# Action Plan Template

| No. | Action | Pillar | Owner | Due date | KPI / evidence | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Appoint ESG lead | Governance | Managing Director | 30 days | Role confirmed in writing | Open |
| 2 | Build GHG baseline | Climate | Finance / ESG Lead | 60 days | Scope 1 and 2 inventory completed | Open |
| 3 | Reduce electricity use 5% | Environment | Operations | 12 months | Monthly kWh trend | Open |
| 4 | Supplier ESG screening | Procurement | Procurement | 6 months | Checklist added to onboarding | Open |
| 5 | Worker welfare review | Social | HR / HSE | 90 days | Corrective actions closed | Open |

# Example Quick Wins for UAE SMEs

Tune cooling set-points and preventive maintenance schedules.

Switch common areas and warehouses to LED lighting and motion sensors.

Track fleet fuel by vehicle and driver; remove avoidable idling.

Ask key suppliers for basic ESG and labour compliance evidence.

Add ESG evidence review to monthly management meetings.

# Monthly Progress Review

| Month | Completed actions | Delayed actions | Decisions needed | Management comments |
| --- | --- | --- | --- | --- |

# Client Tailoring and Evidence Pack

Before issuing this document to a client, replace bracketed fields, confirm the client legal entity name, emirate, licence activity, facilities, sector permits and reporting period. For multi-site clients, prepare one consolidated version plus site-level evidence where the data is materially different.

Authority roles: MOCCAE sets federal climate and environmental policy direction, guidance and national frameworks. Local authorities and regulators, such as Dubai Municipality, Environment Agency - Abu Dhabi (EAD), relevant emirate environmental bodies and Free Zone Authorities including Umm Al Quwain Free Zone or JAFZA, typically administer local environmental permits, inspections, facility-level compliance and sector-specific requirements.

| Tailoring area | What to confirm | Suggested owner |
| --- | --- | --- |
| Company profile | Trade licence, activity list, site list, ownership and operating boundary. | Admin / Legal |
| Compliance context | Applicable UAE federal law, MOCCAE guidance, emirate permits, local inspection requirements, customer requirements, free-zone rules and tender clauses. | Consultant / Compliance |
| Evidence folder | Utility bills, fuel records, waste tickets, HR records, policies, minutes, photos and calculations. | ESG Lead |
| Approval record | Management sign-off, version control, review date and action owners. | Managing Director |

Evidence standard: For every claim, score, action or risk rating, keep a source file or management note. This reduces greenwashing risk and makes the toolkit useful for customer due diligence, tenders, bank requests and regulatory enquiries.

# Reference Sources for Tailoring

UAE Legislation platform, Environment and Natural Resources category, including legislation on safeguarding the environment and reducing the negative effects of climate change.

UAE Ministry of Climate Change and Environment mandate, including climate policy, strategies and initiatives supporting the UAE Net Zero 2050 Strategy.

UAE Net Zero by 2050 Strategic Initiative and UAE Nationally Determined Contribution direction for emissions reduction.

GHG Protocol Corporate Standard and Scope 2 Guidance for organisational greenhouse gas accounting.

ISSB IFRS S1 and IFRS S2, GRI Standards and local market ESG reporting guidance where applicable to listed entities or customer requirements.