Contract Management Procedure

Controls for drafting, review, approval, signature, implementation, renewal, and close-out.

# 1. Objective

To ensure procurement contracts are reviewed before signature, obligations are actively managed, renewals are visible, and supplier performance or risk issues are escalated early.

# 2. Contract Lifecycle

| Stage | Minimum Control | Owner |
| --- | --- | --- |
| Request | Confirm scope, budget, supplier selection route, and contract type. | Requester / procurement |
| Draft | Use approved template where available and include clear deliverables, pricing, VAT, acceptance, and SLA terms. | Procurement |
| Review | Legal review for non-standard, high-value, critical, data, IP, liability, or regulated contracts. | Legal / management |
| Approval | Obtain approval under DoA before signing or issuing PO. | Budget owner / CEO |
| Signature | Only authorized signatories may sign; electronic signature is acceptable if legally and operationally approved. | Authorized signatory |
| Mobilization | Hold kickoff, confirm contract owner, milestones, reporting, insurance, and access requirements. | Contract owner |
| Performance | Track KPIs, deliverables, invoices, claims, changes, risks, and supplier meetings. | Contract owner |
| Renewal/close | Review performance and market options before renewal; document handover and final acceptance at close. | Contract owner / procurement |

# 3. Contract File Requirements

Final signed agreement, appendices, purchase orders, amendments, variation orders, and renewal notices.

Bid/RFQ/RFP documents, evaluation records, award recommendation, and approval evidence.

Supplier registration, trade licence, insurance, VAT/TRN, bank details, and due diligence records.

Key obligation register: deliverables, reports, warranties, termination dates, notice periods, SLAs, penalties/credits, and renewal options.

Performance reviews, service credits, claims, disputes, waivers, and close-out evidence.

# 4. Change and Variation Management

Contract owner identifies the proposed scope, time, price, or risk change.

Supplier submits written variation proposal with pricing, schedule, assumptions, and impact on existing obligations.

Procurement/finance validates pricing and budget availability.

Legal or management reviews any change to liability, IP, data, termination, exclusivity, or governing law.

Approval is obtained under the DoA based on cumulative contract value after the variation.

Work proceeds only after a signed amendment, variation order, or approved PO change.

# 5. Renewal and Termination Controls

Maintain a renewal calendar with alerts at least 90, 60, and 30 days before notice deadlines.

Do not auto-renew without performance review, budget confirmation, and market test or documented exemption.

For termination, confirm notice method, cure periods, data return, asset handover, final invoices, and continuity plan.